## Drum schedule
CABLE DRUM SCHEDULE
Northgate WTW Filter Block B, LV cabling Job HP-2417 Northgate Water (consultant: Aldmoor Consulting Engineers)
Schedule revision: B (2026-09-02) Plan issued: 2026-09-04 for Rev B Printed: 2026-09-28
Cut lengths include 1 m per cut. 2 m kept back on each drum. Offcuts under 15 m count as scrap.
Drum | Cable type | Seq | Cable no. | From | To | Cut (m) | Status | Balance after (m) | Notes
4C × 185 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
DR-01 | 4C × 185 | Received 250 m · balance now 250 m · Laydown A · Anixter UK
|  | 1 | FB-P-001A | LVSB-1 | MCC-B | 97 | To cut | 153
|  | 2 | FB-P-001B | LVSB-1 | MCC-B | 97 | To cut | 56
|  |  | Left on drum |  |  |  |  | 56 | Leftover: reusable
4C × 95 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
DR-02 | 4C × 95 | Received 250 m · balance now 86 m · Laydown A · Anixter UK
|  | ✓ | FB-P-002 | MCC-B | BWP-1 | 79 | Installed |  | 2026-09-08; marks 250 to 171
|  | ✓ | FB-P-003 | MCC-B | BWP-2 | 85 | Cut |  | 2026-09-08; marks 171 to 86
|  |  | Left on drum |  |  |  |  | 86 | Leftover: reusable
4C × 35 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
ST-0412 | 4C × 35 | Received 250 m · balance now 39 m · Laydown A · Ex Hillcrest job
|  | ✓ | FB-P-004 | MCC-B | ASB-1 | 65 | Installed |  | 2026-09-09; marks 176 to 111
|  | ✓ | FB-P-005 | MCC-B | ASB-2 | 72 | Installed |  | 2026-09-09; marks 111 to 39
|  |  | Left on drum |  |  |  |  | 39 | Leftover: reusable
4C × 16 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
DR-03 | 4C × 16 | Received 500 m · balance now 387 m · Laydown A · Anixter UK
|  | ✓ | FB-P-006 | MCC-B | WRP-1 | 113 | Installed |  | 2026-09-10; marks 500 to 387
|  | 1 | FB-P-007 | MCC-B | WRP-2 | 119 | To cut | 268
|  | 2 | FB-P-008 | MCC-B | DB-FB | 56 | To cut | 212
|  |  | Left on drum |  |  |  |  | 212 | Leftover: reusable
4C × 2.5 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
DR-04 | 4C × 2.5 | Received 500 m · balance now 294 m · Filter gallery · Edmundson
|  | ✓ | FB-P-017 | MCC-B | AV-23 | 39 | Installed |  | 2026-09-14; marks 500 to 461
|  | ✓ | FB-P-019 | MCC-B | AV-25 | 37 | Installed |  | 2026-09-14; marks 461 to 424
|  | ✓ | FB-P-023 | MCC-B | AV-34 | 39 | Installed |  | 2026-09-14; marks 424 to 385
|  | ✓ | FB-P-028 | MCC-B | AV-44 | 40 | Cut |  | 2026-09-18; marks 385 to 345
|  | ✓ | FB-P-029 | MCC-B | AV-45 | 51 | Cut |  | 2026-09-18; marks 345 to 294
|  | 1 | FB-P-034 | MCC-B | AV-55 | 53 | To cut | 241
|  | 2 | FB-P-037 | MCC-B | AV-63 | 51 | To cut | 190
|  | 3 | FB-P-033 | MCC-B | AV-54 | 49 | To cut | 141
|  | 4 | FB-P-031 | MCC-B | AV-52 | 48 | To cut | 93
|  | 5 | FB-P-030 | MCC-B | AV-51 | 46 | To cut | 47
|  | 6 | FB-P-032 | MCC-B | AV-53 | 45 | To cut | 2
|  |  | Left on drum |  |  |  |  | 2 | Leftover: scrap
DR-05 | 4C × 2.5 | Received 500 m · balance now 143 m · Filter gallery · Edmundson
|  | ✓ | FB-P-010 | MCC-B | AV-11 | 23 | Installed |  | 2026-09-14; marks 500 to 477
|  | ✓ | FB-P-011 | MCC-B | AV-12 | 28 | Installed |  | 2026-09-14; marks 477 to 449
|  | ✓ | FB-P-012 | MCC-B | AV-13 | 33 | Installed |  | 2026-09-14; marks 449 to 416
|  | ✓ | FB-P-013 | MCC-B | AV-14 | 28 | Installed |  | 2026-09-14; marks 416 to 388
|  | ✓ | FB-P-014 | MCC-B | AV-15 | 31 | Installed |  | 2026-09-14; marks 388 to 357
|  | ✓ | FB-P-015 | MCC-B | AV-21 | 34 | Installed |  | 2026-09-14; marks 357 to 323
|  | ✓ | FB-P-016 | MCC-B | AV-22 | 29 | Installed |  | 2026-09-14; marks 323 to 294
|  | ✓ | FB-P-018 | MCC-B | AV-24 | 32 | Installed |  | 2026-09-14; marks 294 to 262
|  | ✓ | FB-P-020 | MCC-B | AV-31 | 34 | Installed |  | 2026-09-14; marks 262 to 228
|  | ✓ | FB-P-025 | MCC-B | AV-41 | 34 | Cut |  | 2026-09-18; marks 228 to 194
|  | ✓ | FB-P-039 | MCC-B | AV-65 | 51 | Installed |  | 2026-09-16; marks 194 to 143
|  | 1 | FB-P-038 | MCC-B | AV-64 | 56 | To cut | 87
|  | 2 | FB-P-036 | MCC-B | AV-62 | 49 | To cut | 38
|  |  | Left on drum |  |  |  |  | 38 | Leftover: reusable
ST-0388 | 4C × 2.5 | Received 500 m · balance now 44 m · Store · Ex Hillcrest job
|  | ✓ | FB-P-021 | MCC-B | AV-32 | 40 | Installed |  | 2026-09-14; marks 214 to 174
|  | ✓ | FB-P-022 | MCC-B | AV-33 | 40 | Installed |  | 2026-09-14; marks 174 to 134
|  | ✓ | FB-P-024 | MCC-B | AV-35 | 46 | Installed |  | 2026-09-14; marks 134 to 88
|  | ✓ | FB-P-026 | MCC-B | AV-42 | 44 | Cut |  | 2026-09-18; marks 88 to 44
|  | 1 | FB-P-035 | MCC-B | AV-61 | 42 | To cut | 2
|  |  | Left on drum |  |  |  |  | 2 | Leftover: scrap
OC-0391 (offcut) | 4C × 2.5 | Received 38 m · balance now 0 m · Store · Ex Hillcrest job
|  | ✓ | FB-P-027 | MCC-B | AV-43 | 38 | Cut |  | 2026-09-18; marks 38 to 0
|  |  | Left on drum |  |  |  |  | 0 | Leftover: none
12C × 1.5 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
DR-06 | 12C × 1.5 | Received 1000 m · balance now 781 m · Filter gallery · Anixter UK
|  | ✓ | FB-C-001 | MCC-B | LCS-BWP1 | 75 | Installed |  | 2026-09-11; marks 1000 to 925
|  | ✓ | FB-C-002 | MCC-B | LCS-BWP2 | 82 | Cut |  | 2026-09-11; marks 925 to 843
|  | ✓ | FB-C-003 | MCC-B | LCS-ASB1 | 62 | Installed |  | 2026-09-11; marks 843 to 781
|  | 1 | FB-C-006 | MCC-B | LCS-WRP2 | 115 | To cut | 666
|  | 2 | FB-C-005 | MCC-B | LCS-WRP1 | 109 | To cut | 557
|  | 3 | FB-C-012 | PLC-B | FCP-6 | 88 | To cut | 469
|  | 4 | FB-C-011 | PLC-B | FCP-5 | 78 | To cut | 391
|  | 5 | FB-C-004 | MCC-B | LCS-ASB2 | 68 | To cut | 323
|  | 6 | FB-C-010 | PLC-B | FCP-4 | 67 | To cut | 256
|  | 7 | FB-C-009 | PLC-B | FCP-3 | 63 | To cut | 193
|  | 8 | FB-C-008 | PLC-B | FCP-2 | 57 | To cut | 136
|  | 9 | FB-C-007 | PLC-B | FCP-1 | 46 | To cut | 90
|  |  | Left on drum |  |  |  |  | 90 | Leftover: reusable
7C × 1.5 mm² Cu XLPE/SWA/LSZH 0.6/1 kV
DR-07 | 7C × 1.5 | Received 500 m · balance now 217 m · Filter gallery · Edmundson
|  | ✓ | FB-C-024 | FCP-1 | AV-15 | 32 | Installed |  | 2026-09-15; marks 500 to 468
|  | ✓ | FB-C-028 | FCP-2 | AV-24 | 35 | Installed |  | 2026-09-15; marks 468 to 433
|  | ✓ | FB-C-031 | FCP-3 | AV-32 | 34 | Installed |  | 2026-09-15; marks 433 to 399
|  | ✓ | FB-C-033 | FCP-3 | AV-34 | 34 | Installed |  | 2026-09-15; marks 399 to 365
|  | ✓ | FB-C-035 | FCP-4 | AV-41 | 33 | Cut |  | 2026-09-18; marks 365 to 332
|  | ✓ | FB-C-036 | FCP-4 | AV-42 | 39 | Cut |  | 2026-09-18; marks 332 to 293
|  | ✓ | FB-C-037 | FCP-4 | AV-43 | 40 | Cut |  | 2026-09-18; marks 293 to 253
|  | ✓ | FB-C-038 | FCP-4 | AV-44 | 36 | Cut |  | 2026-09-18; marks 253 to 217
|  | 1 | FB-C-044 | FCP-5 | AV-55 | 51 | To cut | 166
|  | 2 | FB-C-047 | FCP-6 | AV-63 | 50 | To cut | 116
|  | 3 | FB-C-046 | FCP-6 | AV-62 | 40 | To cut | 76
|  | 4 | FB-C-045 | FCP-6 | AV-61 | 39 | To cut | 37
|  | 5 | FB-C-040 | FCP-5 | AV-51 | 35 | To cut | 2
|  |  | Left on drum |  |  |  |  | 2 | Leftover: scrap
DR-08 | 7C × 1.5 | Received 500 m · balance now 176 m · Filter gallery · Edmundson
|  | ✓ | FB-C-020 | FCP-1 | AV-11 | 26 | Installed |  | 2026-09-15; marks 500 to 474
|  | ✓ | FB-C-021 | FCP-1 | AV-12 | 28 | Installed |  | 2026-09-15; marks 474 to 446
|  | ✓ | FB-C-022 | FCP-1 | AV-13 | 26 | Installed |  | 2026-09-15; marks 446 to 420
|  | ✓ | FB-C-023 | FCP-1 | AV-14 | 30 | Installed |  | 2026-09-15; marks 420 to 390
|  | ✓ | FB-C-025 | FCP-2 | AV-21 | 24 | Installed |  | 2026-09-15; marks 390 to 366
|  | ✓ | FB-C-026 | FCP-2 | AV-22 | 24 | Installed |  | 2026-09-15; marks 366 to 342
|  | ✓ | FB-C-027 | FCP-2 | AV-23 | 25 | Installed |  | 2026-09-15; marks 342 to 317
|  | ✓ | FB-C-029 | FCP-2 | AV-25 | 30 | Installed |  | 2026-09-15; marks 317 to 287
|  | ✓ | FB-C-030 | FCP-3 | AV-31 | 31 | Installed |  | 2026-09-15; marks 287 to 256
|  | ✓ | FB-C-032 | FCP-3 | AV-33 | 31 | Installed |  | 2026-09-15; marks 256 to 225
|  | ✓ | FB-C-049 | FCP-6 | AV-65 | 49 | Cut |  | 2026-09-16; marks 225 to 176
|  |  | Left on drum |  |  |  |  | 176 | Leftover: reusable
ST-0402 | 7C × 1.5 | Received 500 m · balance now 178 m · Store · Ex Hillcrest job
|  | ✓ | FB-C-034 | FCP-3 | AV-35 | 43 | Installed |  | 2026-09-15; marks 262 to 219
|  | ✓ | FB-C-039 | FCP-4 | AV-45 | 41 | Cut |  | 2026-09-18; marks 219 to 178
|  | 1 | FB-C-043 | FCP-5 | AV-54 | 47 | To cut | 131
|  | 2 | FB-C-041 | FCP-5 | AV-52 | 45 | To cut | 86
|  | 3 | FB-C-048 | FCP-6 | AV-64 | 43 | To cut | 43
|  | 4 | FB-C-042 | FCP-5 | AV-53 | 41 | To cut | 2
|  |  | Left on drum |  |  |  |  | 2 | Leftover: scrap
2P × 1 mm² Cu PVC/SCREENED/SWA/LSZH 300/500 V
DR-09 | 2P × 1 | Received 1000 m · balance now 483 m · Store · Anixter UK
|  | ✓ | FB-I-001 | FCP-1 | LT-101 | 35 | Installed |  | 2026-09-17; marks 1000 to 965
|  | ✓ | FB-I-002 | FCP-1 | AT-101 | 38 | Installed |  | 2026-09-17; marks 965 to 927
|  | ✓ | FB-I-003 | FCP-1 | FIT-101 | 39 | Installed |  | 2026-09-17; marks 927 to 888
|  | ✓ | FB-I-004 | FCP-2 | LT-102 | 39 | Installed |  | 2026-09-17; marks 888 to 849
|  | ✓ | FB-I-005 | FCP-2 | AT-102 | 48 | Installed |  | 2026-09-17; marks 849 to 801
|  | ✓ | FB-I-006 | FCP-2 | FIT-102 | 45 | Installed |  | 2026-09-17; marks 801 to 756
|  | ✓ | FB-I-007 | FCP-3 | LT-103 | 48 | Installed |  | 2026-09-17; marks 756 to 708
|  | ✓ | FB-I-008 | FCP-3 | AT-103 | 52 | Installed |  | 2026-09-17; marks 708 to 656
|  | ✓ | FB-I-009 | FCP-3 | FIT-103 | 47 | Installed |  | 2026-09-17; marks 656 to 609
|  | ✓ | FB-I-013 | FCP-5 | LT-105 | 55 | Installed |  | 2026-09-21; marks 609 to 554
|  | ✓ | FB-I-017 | FCP-6 | AT-106 | 71 | Cut |  | 2026-09-21; marks 554 to 483
|  | 1 | FB-I-018 | FCP-6 | FIT-106 | 68 | To cut | 415
|  | 2 | FB-I-015 | FCP-5 | FIT-105 | 64 | To cut | 351
|  | 3 | FB-I-014 | FCP-5 | AT-105 | 62 | To cut | 289
|  | 4 | FB-I-016 | FCP-6 | LT-106 | 62 | To cut | 227
|  | 5 | FB-I-011 | FCP-4 | AT-104 | 59 | To cut | 168
|  | 6 | FB-I-012 | FCP-4 | FIT-104 | 54 | To cut | 114
|  | 7 | FB-I-010 | FCP-4 | LT-104 | 48 | To cut | 66
|  |  | Left on drum |  |  |  |  | 66 | Leftover: reusable

## Order list
CABLE ORDER LIST
Northgate WTW Filter Block B, LV cabling Job HP-2417 Northgate Water (consultant: Aldmoor Consulting Engineers)
Schedule revision: B (2026-09-02) Plan issued: 2026-09-04 for Rev B Printed: 2026-09-28
Drums the current plan needs beyond the stock on site and on order.
Cable type | Drum length (m) | Qty | Total (m) | £/m | For cables
Nothing to buy: stock on site and on order covers the plan.